## Timeline
Sr No. | Tasks | Sub Tasks | Starting Date | Mitesh Tandel | Anuj Shah | Hitesh Parikh | Yogesh Rathod | Description | Completion Date | Current Status
1 | Analysis | Analysis of project scope, Concept Study, SRS | 2014-06-02 | 6 | 6 | 6 | 6 | Includes login criteria, dashboard arrangment, difficulties in some modules of scope, clarification of some terms in scope, fissibility of the scope modules | 2014-05-07 | Working on it
2 |  | Technical analysis, UX Study, Database Structure Design | 2014-06-09 | 5 | 5 | 5 | 5 | Starting to define different technical modules by analysis, define webservices required for iPhone & Android, DB Structure Design | 2014-05-14 | Not Started
3 | Designing | Wireframe design | 2014-06-16 | 1 | 1 | 1 | 0 | Helping in finazing the Wireframe with respect to programming and module placement | 2014-06-17 | Not Started
4 |  | Database Structure Design Finalization according to final SRS | 2014-06-17 | 2 | 2 | 2 | 0 | Finalizing the DB structure according to final SRS provides | 2014-06-19 | Not Started
5 | Development | Login Development | 2014-06-16 | 0 | 0 | 0 | 2 | Login of user/cop & including webservice for iPhone & Android | 2014-06-18 | Not Started
6 |  | iVolunteer Module Development | 2014-06-18 | 0 | 0 | 0 | 1 | iVolunteer Module Development | 2014-06-19 | Not Started
7 |  | Other Module Developments | 2014-06-19 | 8 | 8 | 8 | 8 | Other Remaining Module Development | 2014-06-30 | Not Started